Yuba County Flock Oversight Project — Master Checklist

Last updated: May 7, 2026 Status key: [x] = Complete | [ ] = Pending / In progress

Data Collection &** Analysis**

- Transparency portal scraper built and running twice daily

  - flock_update.py via LaunchAgent; GitHub repo yuba-county-flock-oversight live with automated commit trail

- >55% blank reason rate confirmed in portal search audit data

  - Post-December 2025 baseline; self-contradiction within YCSO’s own public portal policy statement

- Research summary document consolidated and updated (May 7, 2026)

  - FLOCK_SAFETY_CAMERAS_IN_YUBA_COUNTY v2 produced: >55% blank rate updated throughout; Woodland sharing partner lists (Sections 2a/2b, ~316 agencies) merged; Key Analytical Observations added to Section 4; “What Even a Sanitized Response Reveals” added to Section 5; Section 6 expanded with Phase 2 bridge; Section 10 (Bradford) expanded; Section 11 video review note added; Section 13 Relationship-Building subsection added; Section 14 grassroots engagement note added; Sections 15, 16, 17 carried forward from prior versions

- ~44-45% after-hours search concentration confirmed (10 PM–6 AM Pacific)

  - UTC timezone error caught and corrected; finding is independent of blank rate finding

- Backdated / retroactively added log entries detected

  - 143 total: Backdated entries discovered 16 Mar and then stopped 15 Apr

  - Undermines audit log integrity as an evidentiary argument

- networkCount tier clustering analysis completed

  - 5 apparent tiers identified; expanded regional tier = worst documentation (75.7% blank); presented as open question, not confirmed — pending Flock data dictionary CPRA

- 25-month YCSO Facebook post analysis completed (Jul 2023–Nov 2025)

  - 14,671 total notifications; no causal link to arrests established; YCSO’s own footnote definition used against them

- DOJ crime clearance rate analysis compiled (2015–2024, 10 crime types)

  - Rates dropped during Flock deployment period; attribution problem properly framed; Yuba_Clearance_Rate_Final.xlsx

Legal & Contractual Findings

- Policy 433 vs. contract retention conflict documented

  - Policy says 60-day retention; executed contract purchased up to one year

- SB 34 / Vehicle Code § 2413 compliance gap established

  - Transparency Portal is vendor-controlled, not a compliant agency audit log

- Conflict of interest argument established (dual-track)

  - Gov. Code § 1090 + Yuba County Conflict of Interest Code; Undersheriff Morawczewski chairs oversight committee for funds flowing to his own department

- OMNIA cooperative purchasing contract RS250203 analyzed (April 16, 2026)

  - Three-way retention conflict: Flock 30-day default vs. Policy 433 60-day vs. MSA one-year maximum

  - Flock’s pre-installation permitting coordination commitment strengthens Track B

  - No-proprietary-information certification forecloses trade-secret exemption claims

  - Agency data ownership language prevents YCSO from deflecting SB 34 obligations to Flock

  - MSA Section 3.2: Customer affirmatively warranted compliance with all applicable laws as a signed contract condition – forecloses any argument that December 2025 Flock platform changes transfer SB 34 responsibility to Flock

- YCSO bilateral network sharing confirmed via partner portals (April 20, 2026)

  - YCSO appears as sharing partner on Antioch PD and Woodland PD Transparency Portals

  - Not disclosed on YCSO’s own portal — documentable SB 34 § 2413(b) gap

  - Network spans 224+ agencies; out-of-state reach (Las Vegas Metro, Reno NV) confirmed; NCRIC/WSIN federal fusion centers in granted-access list

  - Documented in research summary Section 17

- YCSO 2025 Annual Report — SB 34 omission finding documented

  - No Flock or ALPR disclosure in annual report; no § 2413 annual report produced publicly

  - Policy 103 Law Enforcement Code of Ethics (“exemplary in obeying the laws of the land”) creates self-contained closing argument

- Flock T&C changes (Feb 2026) and Cal DOJ vs. El Cajon flagged for BOS presentation

  - T&C removed “never sell data” language; added worldwide/perpetuity rights — fiscal stewardship angle

  - AG suing El Cajon over NCRIC data sharing; directly parallels YCSO outside-agency search patterns

- Flock December 2025 system changes documented and implications analyzed

  - Drop-down replacement of free-text; removal of officer names/plate numbers from Network Audit Logs; SB 34 non-compliance risk flagged

- JAG grant conditions reviewed (40, 45, 46, 48)

  - Privacy certificate, 28 C.F.R. Part 23, Justice Information Sharing, facial recognition policy requirements identified

- Measure K Chapter 5.60 governance structure analyzed

  - Trust fund requirement (§5.60.160), annual audit mandate, and oversight committee scope confirmed via Ord. No. 1575

Public Records (CPRA)

- Phase 1 CPRA filed; MSA and Policy 433 produced

  - YCSO cited inapplicable Civil Code § 1798.90.55(b) for withheld records; follow-up drafted

- CPRA 26-136 partial response — OMNIA contract produced April 16, 2026

  - Three categories remain unresolved: authorization/access structure, audit reports/compliance summaries, interagency data sharing agreements

  - YCSO attempted to redirect audit/compliance request to Flock Transparency Portal (documented non-response)

  - April 25, 2026 follow-up trigger: if no further production, send formal constructive denial letter with AG petition notice under § 7923.100

- 26-136 outstanding categories — No documents in response: authorization/access, audit/compliance, interagency sharing

  - Constructive denial letter → Sent and responded.

- Phase 2 CPRA — awaiting Phase 1 completion before filing

  - Targets: unredacted search logs, SB 34 compliance docs, JAG compliance, user access records, hit-to-arrest data

- Phase 3 CPRA — notification-to-enforcement outcome data

  - Connects Facebook notification figures to actual case outcomes; filed after Phase 2 responses in hand

- CPRA to Public Works / Transportation for encroachment permits — filed April 10, 2026

  - Key finding: Public Works MOU covers Starbend Boat Ramp camera only

  - Plumas Lake installations may lack any documented authorization — strategically significant gap

- Flock data dictionary CPRA (networkCount field definitions)

  - Needed to confirm tier clustering inference; currently presented as open question

Presentation & Outreach

- BOS public comment #1 — Flock surveillance oversight argument

  - Lead argument; strongest evidentiary case; June 2026 target; open with “fresh eyes” framing

- BOS public comment #2 — Measure K conflict of interest argument

  - Root cause / structural follow-up; sequenced after Flock appearance

- Poster campaign at Plumas Lake main intersection

  - Factual/structural messaging only; timed to sustain momentum after BOS appearances

- Media outreach (Daily Democrat op-ed target)

  - Timed concurrently with BOS presentation; Phase 2 CPRA response is the tripwire before engagement

- Outreach to DeFlock NorCal — DeFlock NorCal meeting attended April 18, 2026

  - Resources obtained: Woodland audit log data, flagging script, local official contacts from cities that canceled Flock

  - April 25 open meeting scheduled; ongoing coordination underway

- ACLU Northern California — future collaboration consideration

  - After BOS presentation; not before

Outstanding Research Items

- ☐ Quarterly public safety video review

- ☐ Measure K oversight committee reports — full review

- ☐ Hit-to-arrest rate data (most critical missing effectiveness metric)

- ☐ August 2026 San Jose retrospective-search warrant case hearing — monitor for ruling

Strategic Reminders

- Lead with liability at the BOS, not civil liberties

- Two separate public comment appearances: Flock first, Measure K conflict second

- The self-contradiction is the core argument: YCSO’s portal policy statement vs. their own downloadable data

- Blank reason rate and after-hours timing are independent findings — do not conflate

- Research asymmetry is a strategic asset — ask questions, don’t reveal the full evidence stack prematurely

- Structural framing over personal attack at all times

- Incrementalism over intensity: sustained campaign compounds; single punch fades